## Overview
FEATURES
Customers can see parking availablity, register one or more vehicles, see and update info IRT their registered vehicles, and request parking (if available) for any registered vehicle. (A request for parking creates a parking slip.) A customer who has requested parking may check their vehicle's parking status. A customer with a parked vehicle may request that the vehicle be returned. A customer can view their parking history.
Valets are assigned to one parking lot and can see information about available and occupied parking spots at their assigned parking lot. Valets can view and respond to customer requests for parking, view and respond to vehicle return requests, and calculate amount due (which may include discounts) and accept payment.
Owners have one or more parking lots, and can see information about available and occupied parking spots at any or all of their lots. Owners can see financial information for any or all of their lots (based on parking slips).
Users are able to register as a valet or a customer (owners are suumed to get added some other way.) Valets choose their assigned parking lot when registering. Registered users are able to log in and log out. There is an administrative area where users can see their account details and change their password, username, email, or phone.
BUSINESS RULES
Valets can also be customers, but they cannot request parking at their assigned lot
Pricing schedules vary by lot but follow the same structure: hourly rates for weekdays, weekends, and special events
Beyond the 24th hour, all hours parked are charged at a 10% discount
Discounts (including the beyond 24 hour discount, which is applied before any others) are stackable, but discounts beyond the first are taken off the remaining amount, not the original total

## Features
Customer portal | Valet portal | Owner portal | Admin portal
Register as a customer | Register as a valet | Register as an owner | View account details, including assigned roles
LogIn as a customer | LogIn as a valet | LogIn as an owner | Change password
LogOut | LogOut | LogOut | Change username
See registered vehicles | See available and occupied parking for assigned parking lot, including vehicle and customer details for occupied parking spots | See info on owned parking lots | Change email
Add, update, delete registered vehicles | See parking requests | Create, update, and delete owned parking lots/spots | Change phone
View parking availability by parking lot | Process parking requests (advances status from ParkingRequested to VehicleParked) | See financial information for any or all owned parking lots
Request parking at a specific parking lot (if that lot has available parking); creates parking slip with status ParkingRequested | See vehicle pickup requests
See status of a vehicle for which parking has been requested (e.g., has it been parked, if so what spot is it in) | Process vehicle pickup requests (advances status from PickupRequested to VehiclePickedUp, time out, amount due, and amount paid are calculated)
Request pickup of a parked vehicle (advances status from VehicleParked to PickupRequested)
See parking history by vehicle, parking lot, and all history

## Project Architecture
Project | Type | Description
Core | Class library | Cross cutting concerns
Security | Class library | Hash passwords and generate JWTs
API | ASP.NET Core (empty) | Minimal API, EF Core

## Project Plan
Project | Activity | Complate?
Database | Create sample data | Yes
Database | Re-run script | Yes
Database | Create ER diagram | Yes
Core | Verify project is ready to go | Yes
Security | Verify project is ready to go | Yes
API | Create project | Yes
API | Add EF Core nuget packages to project | Yes
API | Scaffold db context and entity classes from db | Yes
API | Review and verify scaffolded db context and entity classes | Yes
API | Create parking status enum | Yes
API | Add parking status prop to parking slip entity, full name prop to user entity | Yes
API | Add ignores and auto includes to db context class | Yes
API | Move db conn string into config | Yes
API | Register the db context in program.cs | Yes
API | Register the jwt middleware in program.cs - password requirements | Yes
Database | Add StateLicensedIn column to vehicles table - combo of this and license plate are unique | Yes
Database | Update sample data in db script to include StateLicensedIn and re-run script | Yes
API | Update vehicle entity to include StateLicensedIn prop | Yes
API | Update db context with StateLicensed in prop configuration for vehicle entity | Yes
API | Review features to determine data needs, in terms of endpoints, dtos | Yes
API | Create dtos, entity-to-dto mappers, and api endpoints | Yes
General | Update README.md | Yes
API | Create register and login endpoints | Yes
Security | Figure out roles | Yes
API | Test register and login endpoints | Yes
API | Add auth to api endpoints, with roles | Yes
API | Re-test all api endpoints, incl. data validity | Yes
API | Create api endpoints for features | No

## Notes
PMC command to scaffold database: | Scaffold-DbContext 'Server=.;Database=ParkAssist;Trusted_Connection=true;Trust Server Certificate=true' Microsoft.EntityFrameworkCore.SqlServer -Tables Customers, Discounts, Owners, ParkingLots, ParkingSlips, ParkingSlipsDiscounts, ParkingSpots, PricingSchedules, Users, Valets, Vehicles -ContextDir Context -OutputDir Models/Entities

## API Endpoint Tests
Endpoint | Auth and roles work? | Data accurate? | Data complete? | username | password | role
Customer | PASS | PASS | PASS | mervin | password123 | customer
LogIn | PASS | PASS | PASS | alice | password123 | valet
Owner | PASS | PASS | PASS | edna | password123 | owner
ParkingLot | PASS | PASS | PASS
ParkingSlip | PASS | PASS | PASS
Register | PASS | PASS | PASS
User | PASS | PASS | PASS
Valet | PASS | PASS | PASS
Vehicle | PASS | PASS | PASS